## vs
VitalSign | Start | End | Task | TaskManager | TaskType | TaskColor | Status | Days | Notes
Water quality | 2024-02-15 | 2024-03-13 | Field preparation | FCL/DMA | Data collection | #00668A | Operational | 30
Water quality | 2024-02-15 | 2024-03-13 | Geospatial data management | GIS | Data collection | #00668A | Operational | 30
Water quality | 2024-03-13 | 2024-05-18 | Field visits & mail samples (Spring) | FCL | Data collection | #00668A | Operational | 10
Water quality | 2024-06-10 | 2024-08-23 | Field visits & mail samples (Summer) | FCL | Data collection | #00668A | Operational | 10
Water quality | 2024-09-09 | 2024-10-31 | Field visits & mail samples (Fall) | FCL | Data collection | #00668A | Operational | 10
Water quality | 2024-12-09 | 2025-02-28 | Field visits & mail samples (Winter) | FCL | Data collection | #00668A | Operational | 10
Water quality | 2024-08-18 | 2024-09-18 | Lab data receipt (Spring) | PM/FCL | Data collection | #00668A | Highly variable (Lab) |  | highly variable
Water quality | 2024-11-23 | 2024-12-23 | Lab data receipt (Summer) | PM/FCL | Data collection | #00668A | Highly variable (Lab) |  | highly variable
Water quality | 2025-02-28 | 2025-03-31 | Lab data receipt (Fall) | PM/FCL | Data collection | #00668A | Highly variable (Lab) |  | highly variable
Water quality | 2025-05-28 | 2025-06-28 | Lab data receipt (Winter) | PM/FCL | Data collection | #00668A | Highly variable (Lab) |  | highly variable
Water quality | 2024-03-22 | 2025-03-07 | Continuous data exported to Aquarius | FCL | Data entry & QA/QC | #AC4F10 | Operational | 350
Water quality | 2024-03-22 | 2025-03-07 | Discrete data entered into SQL database | FCL/DMA | Data entry & QA/QC | #AC4F10 | Needs to be updated | #REF!
Water quality | 2025-03-08 | 2025-04-15 | QA/QC - Continuous data - Aquarius | FCL/PM/DM | Data entry & QA/QC | #AC4F10 | In progress | 30 | water quality lab issues; need to figure out first
Water quality | 2025-03-08 | 2025-04-15 | QA/QC - Discrete data | PM/DM | Data entry & QA/QC | #AC4F10 | In progress | 30 | water quality lab issues; need to figure out first
Water quality | 2025-07-01 | 2025-09-30 | QA/QC - NWQL data | PM/DM | Data entry & QA/QC | #AC4F10 | In progress | 30
Water quality | 2025-09-30 | 2025-10-15 | Validated/Certified data imported into Production SQL database | PM/DM | Data entry & QA/QC | #AC4F10 | In progress | 10
Water quality | 2025-10-15 | 2025-11-15 | Data publication | PM/DM | Data reporting/publication | #7A007A | In progress | 30
Water quality | 2025-10-15 | 2026-05-15 | Data analysis/reporting | PM/DM/GIS | Data reporting/publication | #7A007A | Outstanding | 180
Aquatic macroinvertebrates | 2024-03-01 | 2024-03-31 | Field preparation | FCL/DMA | Data collection | #00668A | Operational | 30
Aquatic macroinvertebrates | 2024-03-01 | 2024-03-31 | Geospatial data management | GIS | Data collection | #00668A | Operational | 30
Aquatic macroinvertebrates | 2024-04-08 | 2024-04-30 | Field visits & mail samples (Spring) | FCL | Data collection | #00668A | Operational | 10
Aquatic macroinvertebrates | 2024-09-01 | 2024-11-15 | Field visits & mail samples (Fall) | FCL | Data collection | #00668A | Operational | 10
Aquatic macroinvertebrates | 2024-07-01 | 2024-08-30 | Lab data receipt (Spring) | PM | Data collection | #00668A | Highly variable (Lab) | 30
Aquatic macroinvertebrates | 2025-02-01 | 2025-04-03 | Lab data receipt (Fall) | PM | Data collection | #00668A | Highly variable (Lab) | 30
Aquatic macroinvertebrates | 2024-04-22 | 2024-05-10 | Field data imported into Development SQL database (Spring) | FCL/DMA | Data entry & QA/QC | #AC4F10 | Operational | 18
Aquatic macroinvertebrates | 2024-09-22 | 2024-11-30 | Field data imported into Development SQL database (Fall) | FCL/DMA | Data entry & QA/QC | #AC4F10 | Operational | 69
Aquatic macroinvertebrates | 2025-04-03 | 2025-05-31 | QA/QC of field and lab data in R | PM/DM | Data entry & QA/QC | #AC4F10 | Operational | 30
Aquatic macroinvertebrates | 2025-05-31 | 2025-06-15 | Validated/Certified data imported into Production SQL database | PM/DM | Data entry & QA/QC | #AC4F10 | Operational | 10
Aquatic macroinvertebrates | 2025-06-15 | 2025-06-30 | Data publication | PM/DM | Data reporting/publication | #7A007A | Operational | 30
Aquatic macroinvertebrates | 2025-06-30 | 2025-12-31 | Data analysis/reporting | PM/DM | Data reporting/publication | #7A007A | Operational | 180 | fix end date to be 6 months
Groundwater | 2024-02-26 | 2024-11-22 | Field preparation/visits | FCL/DMA | Data collection | #00668A | Operational | 10
Groundwater | 2024-02-26 | 2024-11-30 | Field data entered into SQL database (Development) | FCL/DMA | Data entry & QA/QC | #AC4F10 | Future development | 278
Groundwater | 2024-02-26 | 2024-11-30 | Field data imported into Aquarius | FCL | Data entry & QA/QC | #AC4F10 | Operational | 278
Groundwater | 2024-12-01 | 2025-03-01 | Well Elevation Level Assessment | FCL/GIS | Data entry & QA/QC | #AC4F10 | Operational | 90
Groundwater | 2024-12-01 | 2025-03-01 | QA/QC -Discrete data | PM/DM | Data entry & QA/QC | #AC4F10 | In progress | 30
Groundwater | 2024-12-01 | 2025-03-01 | QA/QC - Continuous data - Aquarius | FCL/PM/DM | Data entry & QA/QC | #AC4F10 | In progress | 30
Groundwater | 2024-12-01 | 2025-03-01 | Geospatial Management of Groundwater Sites and Control Points | GIS | Data entry & QA/QC | #AC4F10 | Operational | 30
Groundwater | 2025-03-01 | 2025-03-31 | Validated/Certified data imported into Production SQL database | PM/DM | Data entry & QA/QC | #AC4F11 | In progress
Groundwater | 2025-04-01 | 2025-05-01 | Data publication | PM/DM | Data reporting/publication | #7A007A | In progress | 30
Groundwater | 2025-04-01 | 2025-10-31 | Data analysis/reporting | PM/DM/GIS | Data reporting/publication | #7A007A | Outstanding | 180
Upland vegetation | 2024-01-01 | 2024-01-31 | Field crew hiring | PM/FCL | Data collection | #00668A | Operational | 10
Upland vegetation | 2024-03-15 | 2024-03-31 | Permitting and reporting | PM/FCL | Data collection | #00668A | Operational | 10
Upland vegetation | 2024-04-15 | 2024-05-01 | Field preparation | DMA/FCL/GIS | Data collection | #00668A | Operational | 30
Upland vegetation | 2024-05-01 | 2024-05-07 | Field training | PM/FCL | Data collection | #00668A | Operational
Upland vegetation | 2024-05-09 | 2024-10-24 | Field visits | FCL | Data collection | #00668A | Operational
Upland vegetation | 2024-05-09 | 2024-11-30 | Field data merged into Access database | PM | Data entry & QA/QC | #AC4F10 | Operational
Upland vegetation | 2024-05-09 | 2024-11-30 | QA/QC - Field data paper data sheets | FCL | Data entry & QA/QC | #AC4F10 | Operational
Upland vegetation | 2024-12-01 | 2025-02-28 | QA/QC - Validation scripts | PM | Data entry & QA/QC | #AC4F10 | Operational
Upland vegetation | 2025-03-01 | 2025-03-31 | Validated/Certified data imported into Production SQL database | PM/DM | Data entry & QA/QC | #AC4F11 | Operational
Upland vegetation | 2024-06-01 | 2024-12-31 | Geospatial data management | GIS | Data entry & QA/QC | #AC4F11 | Operational
Upland vegetation | 2025-04-01 | 2025-04-30 | Data publication | PM/DM | Data reporting/publication | #7A007A | Operational
Upland vegetation | 2025-05-01 | 2025-12-31 | Data analysis/reporting | PM/DM/GIS | Data reporting/publication | #7A007A | Operational
Birds | 2024-11-30 | 2025-01-31 | Field crew hiring | PM/IBP | Data collection | #00668A | Operational | 10
Birds | 2024-12-15 | 2025-01-31 | Permitting and reporting | PM/DMA | Data collection | #00668A | Operational | 10
Birds | 2025-02-01 | 2025-03-31 | Field preparation | PM/DMA/GIS | Data collection | #00668A | Operational | 10
Birds | 2025-04-01 | 2025-04-23 | Field training | PM/IBP | Data collection | #00668A | Operational
Birds | 2025-04-25 | 2025-06-30 | Field visits | PM | Data collection | #00668A | Operational
Birds | 2025-07-01 | 2025-09-30 | Field data entered into Access database/Additional data preparation | PM/FCL/GIS/DMA | Data entry & QA/QC | #AC4F10 | Operational | 91
Birds | 2025-09-30 | 2025-10-31 | QA/QC (Access) - Field data validated | PM/DMA/IBP | Data entry & QA/QC | #AC4F10 | Operational | 30
Birds | 2025-11-01 | 2025-11-15 | Validated/Certified data into Access database | PM/DM/DMA | Data entry & QA/QC | #AC4F11 | Operational
Birds | 2025-04-01 | 2025-11-15 | Geospatial data management | GIS | Data entry & QA/QC | #AC4F11 | Operational
Birds | 2025-11-15 | 2025-12-15 | Data publication | PM/DM | Data reporting/publication | #7A007A | Operational | 30
Birds |  |  | Data analysis/reporting | TBD | Data reporting/publication | #7A007A | Outstanding
Note on A44: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: hiring

## wr
VitalSign | Start | End | Task | TaskManager | TaskType | TaskColor | Status | Days | Notes
Water quality | 2024-02-15 | 2024-03-13 | Field preparation | FCL/DMA | Data collection | #00668A | Future development | 30
Water quality | 2024-02-15 | 2024-03-13 | Geospatial data management | GIS | Data collection | #00668A | Operational | 30
Water quality | 2024-03-13 | 2024-05-18 | Field visits & mail samples (Spring) | FCL | Data collection | #00668A | Operational | 10
Water quality | 2024-06-10 | 2024-08-23 | Field visits & mail samples (Summer) | FCL | Data collection | #00668A | Operational | 10
Water quality | 2024-09-09 | 2024-10-31 | Field visits & mail samples (Fall) | FCL | Data collection | #00668A | Operational | 10
Water quality | 2024-12-09 | 2025-02-28 | Field visits & mail samples (Winter) | FCL | Data collection | #00668A | Operational | 10
Water quality | 2024-08-18 | 2024-09-18 | Lab data receipt (Spring) | PM/FCL | Data collection | #00668A | Highly variable (Lab) |  | highly variable
Water quality | 2024-11-23 | 2024-12-23 | Lab data receipt (Summer) | PM/FCL | Data collection | #00668A | Highly variable (Lab) |  | highly variable
Water quality | 2025-02-28 | 2025-03-31 | Lab data receipt (Fall) | PM/FCL | Data collection | #00668A | Highly variable (Lab) |  | highly variable
Water quality | 2025-05-28 | 2025-06-28 | Lab data receipt (Winter) | PM/FCL | Data collection | #00668A | Highly variable (Lab) |  | highly variable
Water quality | 2024-03-22 | 2025-03-07 | Continuous data exported to Aquarius | FCL | Data entry & QA/QC | #AC4F10 | Operational | 350
Water quality | 2024-03-22 | 2025-03-07 | Discrete data imported into Access database | FCL/DMA | Data entry & QA/QC | #AC4F10 | Operational | #REF!
Water quality | 2025-03-08 | 2025-04-15 | QA/QC - Continuous data - Aquarius | FCL/PM/DM | Data entry & QA/QC | #AC4F10 | Needs to be updated | 30 | water quality lab issues; need to figure out first
Water quality | 2025-03-08 | 2025-04-15 | QA/QC - Discrete data | PM/DM | Data entry & QA/QC | #AC4F10 | Needs to be updated | 30 | water quality lab issues; need to figure out first
Water quality | 2025-07-01 | 2025-09-30 | QA/QC - NWQL data | PM/DM | Data entry & QA/QC | #AC4F10 | Needs to be updated | 30
Water quality | 2025-09-30 | 2025-10-15 | Validated/Certified data imported into Production SQL database | PM/DM | Data entry & QA/QC | #AC4F10 | Needs to be updated | 10
Water quality | 2025-10-15 | 2025-11-15 | Data publication | PM/DM | Data reporting/publication | #7A007A | Outstanding | 30
Water quality | 2025-10-15 | 2026-05-15 | Data analysis/reporting | PM/DM/GIS | Data reporting/publication | #7A007A | Outstanding | 180
Aquatic macroinvertebrates | 2024-03-01 | 2024-03-31 | Field preparation | FCL/DMA | Data collection | #00668A | Operational | 30
Aquatic macroinvertebrates | 2024-03-01 | 2024-03-31 | Geospatial data management | GIS | Data collection | #00668A | Operational | 30
Aquatic macroinvertebrates | 2024-04-08 | 2024-04-30 | Field visits & mail samples (Spring) | FCL | Data collection | #00668A | Operational | 10
Aquatic macroinvertebrates | 2024-09-01 | 2024-11-15 | Field visits & mail samples (Fall) | FCL | Data collection | #00668A | Operational | 10
Aquatic macroinvertebrates | 2024-07-01 | 2024-08-30 | Lab data receipt (Spring) | PM | Data collection | #00668A | Operational | 30
Aquatic macroinvertebrates | 2025-02-01 | 2025-04-03 | Lab data receipt (Fall) | PM | Data collection | #00668A | Operational | 30
Aquatic macroinvertebrates | 2024-04-22 | 2024-05-10 | Field data imported into Development SQL database (Spring) | FCL/DMA | Data entry & QA/QC | #AC4F10 | Needs to be updated | 18
Aquatic macroinvertebrates | 2024-09-22 | 2024-11-30 | Field data imported into Development SQL database (Fall) | FCL/DMA | Data entry & QA/QC | #AC4F10 | Needs to be updated | 69
Aquatic macroinvertebrates | 2025-04-03 | 2025-05-31 | QA/QC of field and lab data in R | PM/DM | Data entry & QA/QC | #AC4F10 | Operational | 30
Aquatic macroinvertebrates | 2025-05-31 | 2025-06-15 | Validated/Certified data imported into Production SQL database | PM/DM | Data entry & QA/QC | #AC4F10 | Operational | 10
Aquatic macroinvertebrates | 2025-06-15 | 2025-06-30 | Data publication | PM/DM | Data reporting/publication | #7A007A | Operational | 30
Aquatic macroinvertebrates | 2025-06-30 | 2025-12-31 | Data analysis/reporting | PM/DM | Data reporting/publication | #7A007A | Operational | 180 | fix end date to be 6 months
Groundwater | 2024-02-26 | 2024-11-22 | Field preparation/visits | FCL/DMA | Data collection | #00668A | Operational | 10
Groundwater | 2024-02-26 | 2024-11-30 | Field data entered into SQL database (Development) | FCL/DMA | Data entry & QA/QC | #AC4F10 | Future development | 278
Groundwater | 2024-02-26 | 2024-11-30 | Field data imported into Aquarius | FCL | Data entry & QA/QC | #AC4F10 | Operational | 278
Groundwater | 2024-12-01 | 2025-03-01 | Well Elevation Level Assessment | FCL/GIS | Data entry & QA/QC | #AC4F10 | Operational | 90
Groundwater | 2024-12-01 | 2025-03-01 | QA/QC -Discrete data | PM/DM | Data entry & QA/QC | #AC4F10 | Needs to be updated | 30
Groundwater | 2024-12-01 | 2025-03-01 | QA/QC - Continuous data - Aquarius | FCL/PM/DM | Data entry & QA/QC | #AC4F10 | Needs to be updated | 30
Groundwater | 2024-12-01 | 2025-03-01 | Geospatial Management of Groundwater Sites and Control Points | GIS | Data entry & QA/QC | #AC4F10 | Operational | 30
Groundwater | 2025-03-01 | 2025-03-31 | Validated/Certified data imported into Production SQL database | PM/DM | Data entry & QA/QC | #AC4F11 | Needs to be updated
Groundwater | 2025-04-01 | 2025-05-01 | Data publication | PM/DM | Data reporting/publication | #7A007A | Outstanding | 30
Groundwater | 2025-04-01 | 2025-10-31 | Data analysis/reporting | PM/DM/GIS | Data reporting/publication | #7A007A | Outstanding | 180
Upland vegetation | 2024-01-01 | 2024-01-31 | Field crew hiring | PM/FCL | Data collection | #00668A | Operational | 10
Upland vegetation | 2024-03-15 | 2024-03-31 | Permitting and reporting | PM/FCL | Data collection | #00668A | Operational | 10
Upland vegetation | 2024-04-15 | 2024-05-01 | Field preparation | DMA/FCL/GIS | Data collection | #00668A | Operational | 30
Upland vegetation | 2024-05-01 | 2024-05-07 | Field training | PM/FCL | Data collection | #00668A | Operational
Upland vegetation | 2024-05-09 | 2024-10-24 | Field visits | FCL | Data collection | #00668A | Operational
Upland vegetation | 2024-05-09 | 2024-11-30 | Field data merged into Access database | PM | Data entry & QA/QC | #AC4F10 | Operational
Upland vegetation | 2024-05-09 | 2024-11-30 | QA/QC - Field data paper data sheets | FCL | Data entry & QA/QC | #AC4F10 | Operational
Upland vegetation | 2024-12-01 | 2025-02-28 | QA/QC - Validation scripts | PM | Data entry & QA/QC | #AC4F10 | Operational
Upland vegetation | 2025-03-01 | 2025-03-31 | Validated/Certified data imported into Production SQL database | PM/DM | Data entry & QA/QC | #AC4F11 | Operational
Upland vegetation | 2024-06-01 | 2024-12-31 | Geospatial data management | GIS | Data entry & QA/QC | #AC4F11 | Operational
Upland vegetation | 2025-04-01 | 2025-04-30 | Data publication | PM/DM | Data reporting/publication | #7A007A | Operational
Upland vegetation | 2025-05-01 | 2025-12-31 | Data analysis/reporting | PM/DM/GIS | Data reporting/publication | #7A007A | Operational
Birds | 2024-11-30 | 2025-01-31 | Field crew hiring | PM/IBP | Data collection | #00668A | Operational | 10
Birds | 2024-12-15 | 2025-01-31 | Permitting and reporting | PM/DMA | Data collection | #00668A | Operational | 10
Birds | 2025-02-01 | 2025-03-31 | Field preparation | PM/DMA/GIS | Data collection | #00668A | Operational | 10
Birds | 2025-04-01 | 2025-04-23 | Field training | PM/IBP | Data collection | #00668A | Operational
Birds | 2025-04-25 | 2025-06-30 | Field visits | PM | Data collection | #00668A | Operational
Birds | 2025-07-01 | 2025-09-30 | Field data entered into Access database/Additional data preparation | PM/FCL/GIS/DMA | Data entry & QA/QC | #AC4F10 | Operational | 91
Birds | 2025-09-30 | 2025-10-31 | QA/QC (Access) - Field data validated | PM/DMA/IBP | Data entry & QA/QC | #AC4F10 | Operational | 30
Birds | 2025-11-01 | 2025-11-15 | Validated/Certified data into Access database | PM/DM/DMA | Data entry & QA/QC | #AC4F11 | Operational
Birds | 2025-04-01 | 2025-11-15 | Geospatial data management | GIS | Data entry & QA/QC | #AC4F11 | Operational
Birds | 2025-11-15 | 2025-12-15 | Data publication | PM/DM | Data reporting/publication | #7A007A | Operational | 30
Birds |  |  | Data analysis/reporting | TBD | Data reporting/publication | #7A007A | Outstanding
Note on A44: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: hiring

## wr2
VitalSign | Start | End | Task | SamplingYear | TaskManager | TaskType | TaskColor | Status | Days | Notes
Water quality | 2024-02-15 | 2024-03-13 | Field preparation |  | FCL/DMA | Data collection | #00668A | Future steps | 30
Water quality | 2024-03-13 | 2024-05-18 | Field visits & mail samples (Spring) |  | FCL | Data collection | #00668A | Operational | 10
Water quality | 2024-06-10 | 2024-08-23 | Field visits & mail samples (Summer) |  | FCL | Data collection | #00668A | Operational | 10
Water quality | 2024-09-09 | 2024-10-31 | Field visits & mail samples (Fall) |  | FCL | Data collection | #00668A | Operational | 10
Water quality | 2024-12-09 | 2025-02-28 | Field visits & mail samples (Winter) |  | FCL | Data collection | #00668A | Operational | 10
Water quality | 2024-08-18 | 2024-09-18 | Lab data receipt (Spring) |  | PM | Data collection | #00668A | Highly variable (Lab) |  | highly variable
Water quality | 2024-11-23 | 2024-12-23 | Lab data receipt (Summer) |  | PM | Data collection | #00668A | Highly variable (Lab) |  | highly variable
Water quality | 2025-02-28 | 2025-03-31 | Lab data receipt (Fall) |  | PM | Data collection | #00668A | Highly variable (Lab) |  | highly variable
Water quality | 2025-05-28 | 2025-06-28 | Lab data receipt (Winter) |  | PM | Data collection | #00668A | Highly variable (Lab) |  | highly variable
Water quality | 2024-03-22 | 2025-03-07 | Continuous data exported to Aquarius |  | FCL | Data entry & QA/QC | #AC4F10 | Operational | 350
Water quality | 2024-03-22 | 2025-03-07 | Discrete data imported into Access database |  | FCL/DMA | Data entry & QA/QC | #AC4F10 | Needs to be updated | #REF!
Water quality | 2025-03-08 | 2025-04-15 | QA/QC - Continuous data - Aquarius |  | FCL/PM/DM | Data entry & QA/QC | #AC4F10 | Outstanding | 30 | water quality lab issues; need to figure out first
Water quality | 2025-03-08 | 2025-04-15 | QA/QC - Discrete data |  | PM/DM | Data entry & QA/QC | #AC4F10 | Outstanding | 30 | water quality lab issues; need to figure out first
Water quality | 2025-07-01 | 2025-09-30 | QA/QC - NWQL data |  | PM/DM | Data entry & QA/QC | #AC4F10 | Outstanding | 30
Water quality | 2025-09-30 | 2025-10-15 | Validated/Certified data imported into Production SQL database |  | PM/DM | Data entry & QA/QC | #AC4F10 | Outstanding | 10
Water quality | 2025-10-15 | 2026-05-15 | Data analysis/reporting |  | PM/DM | Data reporting/publication | #7A007A | Outstanding | 180
Water quality | 2026-05-15 | 2026-06-15 | Data publication |  | PM/DM | Data reporting/publication | #7A007A | Outstanding | 30
Aquatic macroinvertebrates | 2024-03-01 | 2024-03-31 | Field preparation |  | FCL/DMA | Data collection | #00668A | Operational | 30
Aquatic macroinvertebrates | 2024-04-08 | 2024-04-30 | Field visits & mail samples (Spring) |  | FCL | Data collection | #00668A | Operational | 10
Aquatic macroinvertebrates | 2024-09-01 | 2024-11-15 | Field visits & mail samples (Fall) |  | FCL | Data collection | #00668A | Operational | 10
Aquatic macroinvertebrates | 2024-07-01 | 2024-08-30 | Lab data receipt (Spring) |  | PM | Data collection | #00668A | Operational | 30
Aquatic macroinvertebrates | 2025-02-01 | 2025-03-03 | Lab data receipt (Fall) |  | PM | Data collection | #00668A | Operational | 30
Aquatic macroinvertebrates | 2024-04-22 | 2024-05-10 | Field data imported into Development SQL database (Spring) |  | FCL/DMA | Data entry & QA/QC | #AC4F10 | Needs to be updated | 18
Aquatic macroinvertebrates | 2024-09-22 | 2024-11-15 | Field data imported into Development SQL database (Fall) |  | FCL/DMA | Data entry & QA/QC | #AC4F10 | Needs to be updated | 54
Aquatic macroinvertebrates | 2025-03-03 | 2025-05-01 | QA/QC of field and lab data in R |  | PM/DM | Data entry & QA/QC | #AC4F10 | Operational | 30
Aquatic macroinvertebrates | 2025-05-01 | 2025-05-15 | Validated/Certified data imported into Production SQL database |  | PM/DM | Data entry & QA/QC | #AC4F10 | Operational | 10
Aquatic macroinvertebrates | 2025-05-15 | 2025-12-15 | Data analysis/reporting |  | PM/DM | Data reporting/publication | #7A007A | Operational | 180 | fix end date to be 6 months
Aquatic macroinvertebrates | 2025-05-01 | 2025-06-01 | Data publication |  | PM/DM | Data reporting/publication | #7A007A | Operational | 30
Groundwater | 2024-02-26 | 2024-11-22 | Field preparation/visits | Y1 | FCL/DMA | Data collection | #00668A | Operational | 10
Groundwater | 2024-02-26 | 2024-11-30 | Field data entered into SQL database (Development) | Y1 | FCL/DMA | Data entry & QA/QC | #AC4F10 | Needs to be updated | 278
Groundwater | 2024-02-26 | 2024-11-30 | Field data imported into Aquarius | Y1 | FCL | Data entry & QA/QC | #AC4F10 | Needs to be updated | 278
Groundwater | 2024-12-01 | 2025-03-01 | QA/QC - Field data | Y1 | PM/DM | Data entry & QA/QC | #AC4F10 | Needs to be updated | 30
Groundwater | 2024-12-01 | 2025-03-01 | QA/QC - Aquarius | Y1 | FCL/PM/DM | Data entry & QA/QC | #AC4F10 | Outstanding | 30
Groundwater | 2025-03-01 | 2025-03-31 | Validated/Certified data imported into Production SQL database | Y1 | PM/DM | Data entry & QA/QC | #AC4F11 | Needs to be updated
Groundwater | 2025-04-01 | 2025-05-01 | Data publication | Y1 | PM/DM | Data reporting/publication | #7A007A | Outstanding | 30
Groundwater | 2025-04-01 | 2025-10-31 | Data analysis/reporting | Y1 | PM/DM | Data reporting/publication | #7A007A | Outstanding | 180
Groundwater | 2025-02-26 | 2025-11-22 | Field preparation/visits | Y2 | FCL/DMA | Data collection | #00668A | Operational | 10
Groundwater | 2025-02-26 | 2025-11-30 | Field data entered into SQL database (Development) | Y2 | FCL/DMA | Data entry & QA/QC | #AC4F10 | Needs to be updated | 277
Groundwater | 2025-02-26 | 2025-11-30 | Field data imported into Aquarius | Y2 | FCL | Data entry & QA/QC | #AC4F10 | Needs to be updated | 277
Groundwater | 2025-12-01 | 2026-03-01 | QA/QC - Field data | Y2 | PM/DM | Data entry & QA/QC | #AC4F10 | Needs to be updated | 30
Groundwater | 2025-12-01 | 2026-03-01 | QA/QC - Aquarius | Y2 | FCL/PM/DM | Data entry & QA/QC | #AC4F10 | Outstanding | 30
Groundwater | 2026-03-01 | 2026-03-31 | Validated/Certified data imported into Production SQL database | Y2 | PM/DM | Data entry & QA/QC | #AC4F11 | Needs to be updated
Groundwater | 2026-04-01 | 2026-05-01 | Data publication | Y2 | PM/DM | Data reporting/publication | #7A007A | Outstanding | 30
Groundwater | 2026-04-01 | 2026-10-31 | Data analysis/reporting | Y2 | PM/DM | Data reporting/publication | #7A007A | Outstanding | 180
Upland vegetation | 2024-01-01 | 2024-01-31 | Field crew hiring |  | PM/FCL | Data collection | #00668A | Operational | 10
Upland vegetation | 2024-03-15 | 2024-03-31 | Permitting and reporting |  | PM/FCL | Data collection | #00668A | Needs to be updated | 10
Upland vegetation | 2024-04-15 | 2024-05-01 | Field preparation |  | DMA/FCL | Data collection | #00668A | Operational | 30
Upland vegetation | 2024-05-01 | 2024-05-07 | Field training |  | PM/FCL | Data collection | #00668A | Operational
Upland vegetation | 2024-05-09 | 2024-10-24 | Field visits |  | FCL | Data collection | #00668A | Operational
Upland vegetation | 2024-05-09 | 2024-11-30 | Field data merged into Access database |  | PM | Data entry & QA/QC | #AC4F10 | Operational
Upland vegetation | 2024-05-09 | 2024-11-30 | QA/QC - Field data paper data sheets |  | FCL | Data entry & QA/QC | #AC4F10 | Operational
Upland vegetation | 2024-12-01 | 2024-02-28 | QA/QC - Validation scripts |  | PM | Data entry & QA/QC | #AC4F10 | Operational
Upland vegetation | 2024-03-01 | 2024-03-31 | Validated/Certified data imported into Production SQL database |  | PM/DM | Data entry & QA/QC | #AC4F11 | Operational
Upland vegetation | 2024-04-01 | 2024-04-30 | Data publication |  | PM/DM | Data reporting/publication | #7A007A | Operational
Upland vegetation | 2024-05-01 | 2024-12-31 | Data analysis/reporting |  | PM/DM | Data reporting/publication | #7A007A | Operational
Birds | 2024-11-30 | 2025-01-31 | Field crew hiring |  | PM/IBP | Data collection | #00668A | Operational | 10
Birds | 2024-12-15 | 2025-01-31 | Permitting and reporting |  | PM/DMA | Data collection | #00668A | Needs to be updated | 10
Birds | 2025-02-01 | 2025-03-31 | Field preparation |  | PM/DMA/GIS | Data collection | #00668A | Needs to be updated | 10
Birds | 2025-04-01 | 2025-04-23 | Field training |  | PM/IBP | Data collection | #00668A | Operational
Birds | 2025-04-25 | 2025-06-30 | Field visits |  | PM | Data collection | #00668A | Operational
Birds | 2025-07-01 | 2025-09-30 | Field data entered into Access database/Additional data preparation |  | PM/FCL/GIS/DMA | Data entry & QA/QC | #AC4F10 | Needs to be updated | 91
Birds | 2025-09-30 | 2025-10-31 | QA/QC (Access) - Field data validated |  | PM/DMA/IBP | Data entry & QA/QC | #AC4F10 | Operational | 30
Birds | 2025-11-01 | 2025-11-15 | Validated/Certified data in Access database |  | PM/DM/DMA | Data entry & QA/QC | #AC4F11 | Operational
Birds | 2025-11-15 | 2025-12-15 | Data publication |  | PM/DM | Data reporting/publication | #7A007A | Outstanding | 30
Birds |  |  | Data analysis/reporting |  | TBD |  |  | Outstanding
Note on A48: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: hiring

## wr_original
VitalSign | Task | TaskType | TaskColor | Status | Start | End | Days | Notes
Water quality | Field preparation | Data collection | #00668A | Future steps | 2024-03-01 | 2024-03-31 | 30
Water quality | Field visits & mail samples (Spring) | Data collection | #00668A | Operational | 2024-03-13 | 2024-05-18 | 10
Water quality | Field visits & mail samples (Summer) | Data collection | #00668A | Operational | 2024-06-10 | 2024-08-23 | 10
Water quality | Field visits & mail samples (Fall) | Data collection | #00668A | Operational | 2024-09-09 | 2024-10-31 | 10
Water quality | Field visits & mail samples (Winter) | Data collection | #00668A | Operational | 2024-12-09 | 2025-02-28 | 10
Water quality | Lab data receipt (Spring) | Data collection | #00668A | Highly variable (Lab) | 2024-08-18 | 2024-09-18 |  | highly variable
Water quality | Lab data receipt (Summer) | Data collection | #00668A | Highly variable (Lab) | 2024-11-23 | 2024-12-23 |  | highly variable
Water quality | Lab data receipt (Fall) | Data collection | #00668A | Highly variable (Lab) | 2025-02-28 | 2025-03-31 |  | highly variable
Water quality | Lab data receipt (Winter) | Data collection | #00668A | Highly variable (Lab) | 2025-05-28 | 2025-06-28 |  | highly variable
Water quality | Lab data imported into SQL database | Data entry & QA/QC | #AC4F10 | Outstanding | 2025-01-01 | 2025-02-28 | 10
Water quality | Lab data imported into SQL database | Data entry & QA/QC | #AC4F10 | Outstanding | 2025-06-01 | 2025-07-31 | 10
Water quality | Continuous data exported to Aquarius (Spring) | Data entry & QA/QC | #AC4F10 | Operational | 2024-03-22 | 2024-05-24 | 63
Water quality | Continuous data exported to Aquarius (Summer) | Data entry & QA/QC | #AC4F10 | Operational | 2024-06-21 | 2024-08-30 | 70
Water quality | Continuous data exported to Aquarius (Fall) | Data entry & QA/QC | #AC4F10 | Operational | 2024-09-20 | 2024-11-08 | 49
Water quality | Continuous data exported to Aquarius (Winter) | Data entry & QA/QC | #AC4F10 | Operational | 2024-12-20 | 2025-03-07 | 77
Water quality | Core parameter data imported into Access database (convert to SQL) | Data entry & QA/QC | #AC4F10 | Needs to be updated | 2024-03-22 | 2024-05-24 | 63
Water quality | Core parameter data imported into Access database (convert to SQL) | Data entry & QA/QC | #AC4F10 | Needs to be updated | 2024-06-21 | 2024-08-30 | 70
Water quality | Core parameter data imported into Access database (convert to SQL) | Data entry & QA/QC | #AC4F10 | Needs to be updated | 2024-09-20 | 2024-11-08 | 49
Water quality | Core parameter data imported into Access database (convert to SQL) | Data entry & QA/QC | #AC4F10 | Needs to be updated | 2024-12-20 | 2025-03-07 | 77
Water quality | QA/QC - Continuous and core parameter data | Data entry & QA/QC | #AC4F10 | Outstanding | 2025-03-01 | 2025-03-31 | 30 | water quality lab issues; need to figure out first
Water quality | QA/QC - NWQL data | Data entry & QA/QC | #AC4F10 | Outstanding | 2025-03-01 | 2025-03-31 | 30
Water quality | Data analysis/reporting | Data reporting/publication | #7A007A | Outstanding | 2025-05-01 | 2025-10-28 | 180
Water quality | Data publication | Data reporting/publication | #7A007A | Outstanding | 2025-10-26 | 2025-11-25 | 30
Aquatic macroinvertebrates | Field preparation | Data collection | #00668A | Operational | 2024-03-01 | 2024-03-31 | 30
Aquatic macroinvertebrates | Field visits & mail samples (Spring) | Data collection | #00668A | Operational | 2024-04-08 | 2024-04-30 | 10
Aquatic macroinvertebrates | Field visits & mail samples (Fall) | Data collection | #00668A | Operational | 2024-09-01 | 2024-11-15 | 10
Aquatic macroinvertebrates | Lab data receipt (Spring) | Data collection | #00668A | Operational | 2024-07-01 | 2024-08-30 | 30
Aquatic macroinvertebrates | Lab data receipt (Fall) | Data collection | #00668A | Operational | 2025-02-01 | 2025-03-03 | 30
Aquatic macroinvertebrates | Lab data imported into SQL database | Data entry & QA/QC | #AC4F10 | Operational | 2025-04-01 | 2025-05-01 | 10
Aquatic macroinvertebrates | Field data imported into SQL database (Spring) | Data entry & QA/QC | #AC4F10 | Operational | 2024-04-22 | 2024-05-10 | 18
Aquatic macroinvertebrates | Field data imported into SQL database (Fall) | Data entry & QA/QC | #AC4F10 | Operational | 2024-09-22 | 2024-11-15 | 54
Aquatic macroinvertebrates | QA/QC | Data entry & QA/QC | #AC4F10 | Operational | 2025-03-03 | 2025-05-01 | 30
Aquatic macroinvertebrates | Data analysis/reporting | Data reporting/publication | #7A007A | Operational | 2025-05-01 | 2025-11-30 | 180 | fix end date to be 6 months
Aquatic macroinvertebrates | Data publication | Data reporting/publication | #7A007A | Operational | 2025-05-01 | 2025-06-01 | 30
Groundwater | Field visits | Data collection | #00668A | Operational | 2024-02-26 | 2024-11-22 | 10
Groundwater | Field data imported into SQL database | Data entry & QA/QC | #AC4F10 | Operational | 2024-02-26 | 2024-11-30 | 278
Groundwater | Field data imported into Aquarius | Data entry & QA/QC | #AC4F10 | Operational | 2024-02-26 | 2024-11-30 | 278
Groundwater | QA/QC | Data entry & QA/QC | #AC4F10 | Outstanding | 2024-12-01 | 2025-02-01 | 30
Groundwater | Data analysis/reporting | Data reporting/publication | #7A007A | Outstanding | 2025-02-01 | 2025-08-31 | 180
Groundwater | Data publication | Data reporting/publication | #7A007A | Outstanding | 2025-02-01 | 2025-03-01 | 30